## Sheet1
Project: Academybugs-ecommerce
BUG ID | MODULE | TITLE | DESCRIPTION | STEPS | EXPECTED RESULT | ACTUAL RESULT | PRIORITY | SEVERITY
BUG_01 | Sign up | The page becomes unresponsive | The page becomes unresponsive when clicking on the Retrieve Password button. | 1.Open a product | The password is sent to the entered email | The page becomes unresponsive when clicking on "Forgot Password" | High | High
2.Scroll down to the Your Account section of the right side menu
3.Click "Sign Up"
4.In the Returning Customer section, click "Forgot Your Password?"
5.Enter your email in the field and click "Retrieve Password"
BUG_02 | Product detail | Currency dropdown not working in the | The page freezes when changing the currency | 1.Click the Find Bugs link on the navigation bar | The currency is changed as expected | The page freezes when changing the currency | High | Medium
|  | product details page |  | 2.Open a product
3.Change the currency in the right side menu
BUG_03 | Product detail | view button not working in the | the page becomes unresponsive when clicking on view button. | 1.Click the Find Bugs link on the navigation bar | The selected number of results is displayed according to the clicked buttons | The page freezes when clicking on view | High | Medium
|  | product details page |  | 2.Click on the View buttons in product listing page to show a certain number of results at the top left
BUG_04 | Product detail | unable to post comments in the comments | The page becomes unresponsive when clicking on the Post Comment button | 1.Open a product | The comment is posted under the product | The page becomes unresponsive when clicking on "Post Comment" | Medium | High
|  | section on the product details page. |  | 2.Scroll down to the Leave a Reply section
3.Fill out the comment form
4.Click "Post Comment"
BUG_05 | Cart | Product quantity issue | the product quantity cannot be increased 2 | 1.Add one or more products to the cart | The product quantity can be increased 2 | When clicking on the update button, | High | High
|  |  |  | 2.Click the "View cart" link at the top of the page |  | the product quantity becomes 2 again
3.Set the product quantity to 3 or more
4.Click "update" below
BUG_06 | Cart | Grand total calculation in cart is wrong | Grand total calculation issue is wrong | 1.Add one or more products to the cart | The grand total is equal to the sum of all products in the cart | The grand total is wrong | High | High
2.Click the "View cart" link on top of the page
BUG_07 | Product detail | Manufacture link not working in the | the manufacturer link in the product details page is broken | 1.Open a product | The manufacturer link shows an appropriate page | The manufacturer link opens an error page | High | Medium
|  | product details page |  | 2.Click the manufacturer link under the quantity
BUG_08 | Product listing | Product image layout is misaligned | Some product image is not completely displayed | 1.Click the Find Bugs link on the navigation bar | The product image fills the box entirely | The image has a white space on the right | Medium | Low
2.Click on "Dark Grey Jeans"
BUG_09 | Product Detail page | Twitter share button in the | Twitter share button in the product details page is broken. | 1.Click the Find Bugs link on the navigation bar | The Twitter share button shows an appropriate page | The Twitter share button shows an error page | Medium | Medium
|  | product details page is broken |  | 2.Open a product
3.Click the Twitter share button
BUG_10 | Sign-In | Sign In button is misaligned vertically. | the caption of the Sign In button is misaligned vertically. | 1.Click the Find Bugs link on the navigation bar | The caption of the Sign In button | The caption of the Sign In button | Low | Low
|  |  |  | 2.Open a product | is centred vertically | is misaligned vertically
3.Scroll to the bottom and find the sign in
form in the right side menu
4.Enter any login and password that are
not registered and click "Sign In"
BUG_11 | Sign-In | the title of the password field is misaligned | the title of the password field is misaligned to the right side | 1.Click the Find Bugs link on the navigation bar | The title of the password field is aligned | The title of the password field is | Low | Low
|  |  |  | 2.Open a product | the same as the field above | not aligned the same as the field above
3.Scroll down to the bottom of the right side menu
4.Click "Sign In" without filling the form to open
the Sign In page
BUG_12 | Prouduct detail page | Description of the product are not in English | the short description and description of the product are not in English | 1.Click the Find Bugs link on the navigation bar | The short description and description of the | The short description and description of the | Medium | Medium
|  |  |  | 2.Open a product | product are in English | product are not in English
BUG_13 | Sign-In | Text under the New User section is not in English. | Text under the New User section is not in English. | 1.Click the Find Bugs link on the navigation bar | The text under the New User section is in English | The text under the New User section is not in English | Low | Low
2.Open a product
3.Scroll down to the bottom of the right side menu
4.Click "Sign In" to open the sign in page
BUG_14 | Payment Page | Billing address in payment section didn't load properly | The billing address in the payment section failed to load correctly | 1.Open a product | The Billing Address section shows appropriate info | The Billing Address section loads endlessly. | Medium | Medium
2.Sign up if you are not signed up or log in at the bottom of right side menu
3.At the bottom of the right side menu select Dashboard
4.Scroll up to the Billing Address section